## Template
Project objectives | Deliverable | Business requirements | Solution requirements | Use case | Verified | Verified By | Validated | Validated By | Acceptance Criteria | Test Case | Test Case Description | Expected Outcomes | Actual Outcomes | Status | Notes

## Course_Example
Project objectives | Deliverable | Business requirements | Solution requirements | Use case | Verified | Verified By | Validated | Validated By | Acceptance Criteria | Test Case | Test Case Description | Expected Outcomes | Actual Outcomes | Status | Notes
Website upgrade | Upgraded website | Subscription feature | Notification of promotions | A user can sign up to be notified of sales | Yes | Project team | Yes | Sponsor | Ability to select Sales Promotion as a type of subscription | Subscription type Sales | Able to select a type of subscription as Sales Promotion | When subscribing, user able to select Sales Promotions as type of subscription | Tester able to select Sales Promotions under type of subscription | Pass
Website upgrade | Upgraded website | Subscription feature | Self-subscribe | A [potential] customer can go to the website and select to be notified of new sales and specials | Yes | Project team | Yes | Sponsor | User able to enter email address on website and select "Subscribe" for Sales Promotions | Subscription email | Enter email when subscribing to sales promotions | When subscribing, user is prompted to enter email before selecting subscription | Tester was able to submit before entering email address | Fail
Website upgrade | Upgraded website | Subscription feature | Available on mobile devices | Subscribe via smartphone | Yes | Project team | Yes | Sponsor | User can access website from smart phone and select subscribe to Sales Promotions, entering email address and confirming on smart phone | Access via smartphone | Website is accessible from a smart phone and displays all website features | On a smart phone, navigation and menus, subscription feature, reservations, and amenities' views all display |  | Not started
Website upgrade | Upgraded website | Subscription feature | Available on mobile devices | Subscribe via smartphone | Yes | Project team | Yes | Sponsor | User can access website from smart phone and select subscribe to Sales Promotions, entering email address and confirming on smart phone | Subscribe to Sales Promotions via smart phone | On smart phone, can select subscribe to Sales Promotions, able to enter email address and select subscribe; confirmation screen then shows to user | User gets confirmation of subscription on smart phone |  | In progress
Website upgrade | Upgraded website | Subscription feature | Available on mobile devices | Access via tablet | Yes | Project team | Yes | Sponsor | User can access website from tablet and select subscribe to Sales promotions, entering email address and confirming on tablet | Subscribe to Sales Promotions via tablet | On tablet, can select subscribe to Sales Promotions, able to enter email address and select subscribe; confirmation screen then shows to user | User gets confirmation of subscription on a tablet |  | Not started
Website upgrade | Upgraded website | Amenities interactive images | 360 degree photos | Potential customer can see what the gym and pool look like at a particular location | Yes | Project team | Yes | Sponsor | User can select a property and select amenities with an option to view 360 degree single image that a user can pan left or right with navigation arrows to see entire space | 360 degree image | User can get a 360 degree view of a property amenity that pans left and right to view full amenity | When select a property amenity, the 360 degree image "click here" displays. Upon clicking, user is able to pan left or right for full 360 degree view of amenity |  | Not started
Website upgrade | Training | Employees know how to update new website | User manual | IT has desk reference to look up how to update a feature | Yes | Project team | Yes | Sponsor | User manual identifies all website features with detailed, explicit steps of how to add, edit, and delete entries in each feature | User manual | User manual has step by step instructions on how to change features | User able to change a feature following the instructions in the user manual |  | Not started
Website upgrade | Marketing | Advertise new features | New features are highlighted to returning website users | Returning users check out the new features | Yes | Project team | Yes | Sponsor | Website able to acknowledge a returning user and highlights any features that were not present the last time the user visited the website | Returning user new features | Returning users to the website are prompted to check out new features | A user who has visited the website before is prompted to "Check out new features" that they can accept or close the window and proceed |  | Not started
Website upgrade | Upgraded website | Ability to easily add new features | Test and development site | Able to add a new feature to only one section of the website | Yes | Project team | Yes | Sponsor | Technology can build and test a new feature without interrupting or affecting production website | New feature build | New features can be built and tested with out affecting production website | Technology team can build, test, and deploy a new feature without any impact to other areas of website where feature is not being deployed to |  | Not started